VoxAngelos Project Completion Timeline July 1 – August 31, 2026 ¦ Target Completion: August 31, 2026

TEAM MEMBERS

|  | Rhianna (Project Lead / Full-stack) |  | Nicole (Backend / NLP) |  | Lorenzo (Frontend / UI-UX) |
| --- | --- | --- | --- | --- | --- |

PHASE 1 ¦ July 1 – 15, 2026 ¦ Foundation & NLP Testing

Focus: Get the NLP to 75% accuracy and begin UI/UX revision planning.

| Task | Assignee | Priority |
| --- | --- | --- |
| Submit 500 test concerns to the system for NLP classification testing | Nicole + Rhianna + Lorenzo | HIGH |
| Track NLP classification results — log correct vs incorrect categorizations | Nicole | HIGH |
| Retrain / fine-tune NLP model based on misclassified results | Nicole | HIGH |
| Implement NLP routing for Recommendations (auto-assign to LGU dept) | Nicole | HIGH |
| Audit current UI/UX across all pages — document pain points and panelist feedback | Lorenzo | HIGH |
| Create UI/UX revision mockups / wireframes for revised design | Lorenzo | HIGH |
| Fix cloud file storage — migrate wwwroot/uploads to Azure Blob or Cloudinary | Rhianna | HIGH |
| Fix duplicate NuGet packages in VoxAngelos.csproj | Rhianna | MEDIUM |

PHASE 2 ¦ July 15 – 31, 2026 ¦ UI Overhaul & Leaderboard Formula

Focus: Apply revised UI/UX across the system and implement the new leaderboard scoring formula.

| Task | Assignee | Priority |
| --- | --- | --- |
| Apply revised UI/UX design to Citizen side (Discover, Create, Notifications, Profile) | Lorenzo | HIGH |
| Apply revised UI/UX design to LGU side (Dashboard, Concerns, Leaderboard, Heatmap) | Lorenzo | HIGH |
| Apply revised UI/UX design to Admin side | Lorenzo | MEDIUM |
| Design and implement new Leaderboard scoring formula | Rhianna | HIGH |
| Replace upvote-only sorting with new formula in both Citizen and LGU Leaderboard ( | Rhianna | HIGH |
| Continue NLP accuracy testing — aim to hit 75% threshold | Nicole | HIGH |
| Full recommendation flow test: submit → LGU review → publish → citizen discover | Rhianna | HIGH |
| Add manual |  |  |

PHASE 3 ¦ August 1 – 15, 2026 ¦ Testing & QA

Focus: Full system testing, bug fixing, and quality assurance across all roles.

| Task | Assignee | Priority |
| --- | --- | --- |
| End-to-end testing — Citizen registration, concern submission, recommendation flow | Lorenzo | HIGH |
| LGU workflow testing — concern feed, status updates, review recommendations | Rhianna | HIGH |
| Admin workflow testing — user approvals, office management | Nicole | MEDIUM |
| NLP classification accuracy validation — confirm 75% achieved, document results | Nicole | HIGH |
| Leaderboard formula testing — verify scoring is consistent and fair | Rhianna | HIGH |
| Cross-browser and mobile responsiveness testing | Lorenzo | MEDIUM |
| Load/performance testing — simulate multiple concurrent users | Nicole + Rhianna + Lorenzo | MEDIUM |
| Security check — confirm antiforgery tokens, auth policies, file upload validation | Lorenzo | HIGH |
| Fix all bugs identified during QA phase | Rhianna + Nicole + Lorenzo | HIGH |
| Deploy tested build to Render — verify PostgreSQL migrations are applied | Nicole | HIGH |

PHASE 4 ¦ August 15 – 31, 2026 ¦ Final Polish & Submission

Focus: Final refinements, documentation, and preparation for defense/submission.

| Task | Assignee | Priority |
| --- | --- | --- |
| Final UI polish — spacing, typography, color consistency across all pages | Lorenzo | HIGH |
| Prepare system documentation and user manual | Lorenzo | HIGH |
| Record system demo video(if needed) | Rhianna + Lorenzo + Nicole | HIGH |
| Prepare final presentation / slides for panelists | Rhianna + Lorenzo + Nicole | HIGH |
| Regression testing — ensure no new bugs after final polish | Rhianna + Lorenzo + Nicole | HIGH |
| Final deployment — production build live on Render | Nicole | HIGH |
| Submit all deliverables | Rhianna + Lorenzo + Nicole | HIGH |

PANELIST NOTE: Leaderboard Scoring Formula Recommendation

The current leaderboard ranks by raw upvote count. Panelists recommend a more sophisticated formula. A suggested approach is the Wilson Score Interval, which accounts for both upvotes and downvotes while adjusting for low vote counts:

Score = (upvotes + 1.9208) / (upvotes + downvotes) – 1.96 × sqrt((upvotes × downvotes / (upvotes + downvotes)) + 0.9604) / (upvotes + downvotes + 3.8416) Alternatively, a simpler weighted formula: Score = Upvotes – (Downvotes × 0.5) + (RecencyBoost) Where RecencyBoost = a small bonus for recommendations submitted within the last 30 days.

MILESTONE SUMMARY

| Phase | Dates | Goal |
| --- | --- | --- |
| Phase 1 | July 1 – 15 | NLP Testing + UI Audit |
| Phase 2 | July 15 – 31 | UI Overhaul + Leaderboard Formula |
| Phase 3 | August 1 – 15 | Full Testing & QA |
| Phase 4 | August 15 – 31 | Final Polish + Submission |

Revisions

Auto-delete images/videos after 3 days

Real-time updates (no refresh)

500 NLP test concern submissions

NLP feedback buttons (Correct/Incorrect) for LGU

Fix citizen-side map - rhi

Responsive mobile view for citizen-side - tan

VoxAngelos — Angeles City, Pampanga, Philippines   |   Target Completion: August 31, 2026